NexTime

Project & Timesheet System

User & System Guide

URL: https://vibeproject.online

Date: June 23, 2026  |  Version 1.0

# Table of Contents

# 1. System Overview

NexTime is a web-based Project & Timesheet System that enables teams to track projects, manage tasks using Agile methodologies, log working hours, and generate HR & Cost reports — all in one place.

## 1.1 System Access Information

| System Name | NexTime — Project & Timesheet System |
| --- | --- |
| URL | https://vibeproject.online |
| Developer | Antigravity (ATGV) |
| Type | Web Application (compatible with all browsers) |

## 1.2 Key Features

| Module | Description | Primary Users |
| --- | --- | --- |
| Dashboard | KPI overview and project status summary | All roles |
| Projects | Create and manage projects | Admin / PM |
| Project Plan | Gantt Chart and Milestone Timeline | Admin / PM |
| Tasks & Agile Planner | Backlog, Kanban Board, Timeline | All roles |
| Timesheet | Log daily working hours | All roles |
| Team & Approvals | Manage team members and approve timesheets | Admin / PM |
| HR & Cost Reports | Time usage and cost reports | Admin / PM |
| System Settings | Configure templates, permissions, and labor rates | Admin |

Chapter 2: Dashboard

# 2. Dashboard

The Dashboard provides a real-time overview of project status and user tasks immediately after login.

Figure 2.1 — Dashboard showing Summary Cards and Overdue Tasks

## 2.1 Summary Cards

| Card | Description |
| --- | --- |
| Active Projects | Number of active projects the user is a member of |
| My Active Tasks | Number of incomplete tasks (not in Done status) |
| Overdue Tasks | Number of tasks past their due date — displayed in red |
| Hours This Week | Hours logged in Timesheet over the last 7 days |

## 2.2 Overdue Tasks Section

Displays overdue task details grouped by Project and Priority (Urgent / High / Medium).

## 2.3 My Tasks & Project Health

User tasks sorted by Due Date, and Project Health cards showing Progress %, team members, and overdue dates.

Chapter 3: Projects

# 3. Projects

The Projects page displays all projects in a Card View layout.

Figure 3.1 — Projects page showing all project cards

## 3.1 Project Card Information

| Component | Details |
| --- | --- |
| Project Name | e.g. TWD_LON, NexTime Internal Tool |
| Status Badge | Active (green) or Planning (yellow) |
| Dates | Project start date – end date |
| Budget | Project budget, e.g. $250,000 |
| Team | Number and avatars of team members |
| Plan | Link to the Auto-Generated Plan (Milestones) |

## 3.2 Current Projects in System

| Project | Status | Budget | Timeline |
| --- | --- | --- | --- |
| TWD_LON | Active | $250,000 | 10/06 – 29/05/2026 |
| TWD_SVC | Planning | – | 01/01 – 01/08/2026 |
| CFW_OI | Planning | – | 01/05/2025 – 31/08/2026 |
| TWD_Support | Planning | – | 11/06 – 11/12/2026 |
| cds_stk | Planning | – | 01/06 – 15/11/2026 |
| E-Commerce Platform Redesign | Planning | – | 15/07/2026 – Ongoing |
| Next time | Planning | $5,000,000 | 05/06 – 10/07/2026 |
| NexTime Internal Tool | Active | $50,000 | 01/06 – 30/08/2026 |

## 3.3 Creating a New Project

Click '+ New Project' in the top-right corner. The system will automatically generate an Auto-Generated Plan with 11 standard milestones.

Chapter 4: Project Plan & Timeline

# 4. Project Plan & Timeline

Used to track milestones and compare the Base Plan against the Current Live Plan via a Gantt Chart.

Figure 4.1 — Project Plan & Timeline showing Gantt Chart and Drift Metrics

## 4.1 Drift Metrics

| Metric | Description |
| --- | --- |
| Schedule Slippage (Drift) | Number of days delayed from original plan — green = On Track |
| Estimate Drift | Hours added or reduced from original estimate |
| Story Points Drift | Story Points changed from original plan |
| Approved Actual Hours | Actual hours logged and approved from Timesheet |

## 4.2 Standard 11-Step Milestones

| # | Milestone | Phase (%) | Default Est. |
| --- | --- | --- | --- |
| 1 | Kick off Meeting | 0–2% | 4h |
| 2 | SOW & Contract Sign off | 2–6% | 8h |
| 3 | Get Requirements & User Stories | 6–20% | 16h |
| 4 | UX/UI Design & Prototyping | 20–35% | 24h |
| 5 | Setup Cloud Infrastructure & Environments | 25–32% | 12h |
| 6 | API Contract & Backend Architecture Setup | 32–40% | 16h |
| 7 | Core Backend & Frontend Development | 40–75% | 40h |
| 8 | Data Migration & Seeding | 70–75% | 16h |
| 9 | SIT (System Integration Testing) | 75–85% | 16h |
| 10 | UAT (User Acceptance Testing) | 85–95% | 24h |
| 11 | Production Release & Handover | 95–100% | 8h |

Chapter 5: Tasks & Agile Planner

# 5. Tasks & Agile Planner

The primary module for task management, supporting Sprints, Backlog, Kanban Board, and Timeline views.

Figure 5.1 — Tasks & Agile Planner showing Summary and Team Workload

## 5.1 Tabs and Views

| Tab | Details |
| --- | --- |
| Summary | KPI overview: TO DO / IN PROGRESS / REVIEW / DONE + Team Workload + Upcoming Tasks |
| Backlog | All tasks awaiting a Sprint — Sprints can be started from this tab |
| Board | Kanban Board with 4 columns; drag and drop tasks between columns |
| Timeline | Gantt-style view for visualizing tasks over time |

## 5.2 Current Task Statistics (All Projects)

| Status | Count |
| --- | --- |
| TO DO | 81 |
| IN PROGRESS | 54 |
| REVIEW | 13 |
| DONE | 11 |
| Total | 159 Tasks |

## 5.3 Adding a New Task

Click '+ Add Task' → Fill in: Task name, Project, Priority (Urgent/High/Medium/Low), Assignee, Due Date, Story Points.

Chapter 6: Timesheet

# 6. Timesheet

Log daily working hours and track approval status from the PM.

Figure 6.1 — Timesheet showing Calendar View, Monthly Summary and Approval Status

## 6.1 Logging Time

Select a date on the calendar → Click '+ Log Time' → Fill in: Date, Project, Hours, Description.

## 6.2 Monthly Summary

| Field | Description |
| --- | --- |
| Total Logged | Total hours logged for the month |
| Target | Monthly hour target (default 160h) |

## 6.3 Approval Status

| Status | Description |
| --- | --- |
| Approved (green) | Hours that have been approved by PM/Admin |
| Pending (orange) | Awaiting PM approval |

Chapter 7: Team & Approvals

# 7. Team & Approvals

Manage team member information and approve timesheets submitted by employees.

Figure 7.1 — Team & Approvals showing Team Directory and all members

## 7.1 Team Directory

Each card displays: Name, Role, Email, Skills, and assigned Project Roles.

## 7.2 Pending Approvals

PM/Admin can approve or reject timesheets from the 'Pending Approvals' tab (red badge shows the number of pending items).

## 7.3 Current Team Members (11 people)

| Name | Role | Primary Project |
| --- | --- | --- |
| isarachootip | Admin • Management | – |
| Polakrit | Employee • outsource | NexTime Internal Tool (PM) |
| Naruedom Mukkhan | Employee • Special Project | TWD_Support, cds_stk (Lead) |
| Kridsada Somwong | Employee • special project | cds_stk (Frontend dev) |
| Pailin Chompun | Employee • special project | TWD_SVC, TWD_Support |
| Jitpanu Thepsuya | Employee | TWD_LON, TWD_Support |
| Sakda Ruengthong | Employee • special project | TWD_SVC (PM), TWD_Support |
| Natchaphon Jumnakros | Employee • special project | TWD_SVC (Lead), TWD_Support |
| Isara Ch. | Employee • Engineering | NexTime Internal Tool, cds_stk |

Chapter 8: HR & Cost Reports

# 8. HR & Cost Reports

Analyze team time utilization, project costs, and individual performance.

Figure 8.1 — HR & Cost Reports showing Overview: Time Allocation and Resource Hours

## 8.1 Key Metrics

| Metric | Description |
| --- | --- |
| Total Logged Hours | Total hours logged in the selected period |
| Approved Hours | Approved hours / total hours |
| Approval Rate | Percentage of hours approved |
| Time Allocation by Project | Time distribution broken down by project |
| Resource Hours Summary | Total hours per individual team member |

## 8.2 Report Tabs

| Tab | Details |
| --- | --- |
| Overview | Summary: Time Allocation, Resource Hours, Timesheet Calendar |
| Personal Performance | Individual performance metrics per team member |
| Project Cost | Project cost calculated from Hours × Labor Rate |

## 8.3 Export

Export as CSV (for Excel analysis) or PDF (formal report) using the button in the top-right corner.

## 8.4 Current Data (June 2026)

| Data | Value |
| --- | --- |
| Total Logged | 70.5h (13 entries) |
| Approved | 14h (20%) |
| Top Project by Hours | NexTime Internal Tool — 45h (64%) |

Chapter 9: System Settings

# 9. System Settings

Used by Admin to configure system-wide settings, including project plan generation, access permissions, and labor rates.

Figure 9.1 — System Settings showing Milestone Templates and Visual Timeline Preview

## 9.1 Milestone Templates

Define standard milestones that are auto-generated when a new project is created. Click '+ Add Milestone Template' to add new ones.

## 9.2 Git Webhook Integrations

Connect GitHub/GitLab repositories to projects for automatic commit and deployment tracking.

## 9.3 Permission Schemes

Define access rights for each module per role.

## 9.4 Labor Rates

Set hourly labor rates by employee type — used to calculate Project Cost in reports.

Chapter 10: FAQ & Appendix

# 10. Frequently Asked Questions (FAQ)

| Question | Answer |
| --- | --- |
| Can I log timesheet entries for past dates? | Yes — select the date on the calendar and click Log Time. |
| Why is my Timesheet stuck in Pending? | It is awaiting approval from PM/Admin via the Team & Approvals page. |
| What should I do when a task shows as Overdue? | Update the task status to Done, or request a Due Date extension from the PM. |
| What is an Auto-Generated Plan? | A plan automatically created by the system from the Milestone Template defined in Settings. |
| What is a Sprint? | A development cycle of 1–4 weeks. Sprints can be started from the Backlog tab. |
| What export formats are available for reports? | CSV (Excel) and PDF — use the button in the top-right corner of the Reports page. |

# Appendix: Main Page URLs

| Page | URL |
| --- | --- |
| Dashboard | https://vibeproject.online/ |
| Projects | https://vibeproject.online/projects |
| Project Plan | https://vibeproject.online/project-plan |
| Tasks | https://vibeproject.online/tasks |
| Timesheet | https://vibeproject.online/timesheet |
| Team | https://vibeproject.online/team |
| Reports | https://vibeproject.online/reports |
| Settings | https://vibeproject.online/settings |

— End of NexTime User & System Guide —

NexTime v1.0  |  Antigravity (ATGV)  |  June 2026